## 00_Readme
PACER Research Tracker — Pro Edition
Research control workbook ¦ proposal → literature → datasets → experiments → evidence
PACER Research Tracker — Pro Edition
Purpose | A research-management workbook for the PACER proposal: prediction-conditioned retrieval/compression/cache resource allocation for low-latency RAG on local open-source LLMs.
How to use | Start with Dashboard. Maintain literature in Literature Matrix, datasets in Dataset Registry, experiments in Experiment Matrix, and ablations in Ablation Matrix.
Core novelty framing | Do NOT claim that predictive retrieval, adaptive compression, or KV caching are individually novel. Track PACER as a coordination/resource-allocation policy under a common latency–quality budget.
Primary evaluation regime | Single consumer GPU / local open-source LLMs, with explicit TTFT, E2E latency, throughput, memory, quality, and overhead reporting.
Evidence rule | Every literature claim should have a source URL/DOI/arXiv identifier and a clear evidence/limitation note.
Status legend | Planned / In Progress / Reproduced / Validated / Blocked / Not Applicable
Workbook design | Black-and-white professional base theme; light fills are used only for status/priority readability.

## 01_Dashboard
PACER Research Dashboard
One-page control center for proposal execution and evidence quality
Metric | Value | Interpretation
Literature records | 17 | Core systems/compression/prefetch/cache papers tracked
Datasets registered | 15 | Text + multimodal/visual evaluation candidates
Experiment rows | 18 | Planned baseline, component, full-system, and stress tests
Ablation rows | 8 | S0–S7 controlled component isolation
Open risks | 8 | Research risks requiring mitigation
Primary research question | Prediction-conditioned resource allocation | Jointly decide retrieval, compression, and reuse under a latency/quality budget
Primary evaluation hardware | Single 24GB-class consumer GPU | Avoid data-center-only conclusions
Core models | Qwen3-8B; Llama-3.2-3B/8B | Local open-source inference regime
Workstream | Target | Status
Literature | Close novelty gaps; verify claims | In Progress
Datasets | Lock primary + multimodal extension | In Progress
Baselines | Reproduce strongest comparable systems | Planned
PACER policy | Train/evaluate joint allocation policy | Planned
Ablations | S0–S7 with paired seeds | Planned
Statistics | Bootstrap + Wilcoxon + Holm correction | Planned
Reproducibility | Config + hardware + seeds + logs | Planned

## 02_Literature_Matrix
PACER Literature Matrix
Evidence-oriented literature review with explicit overlap and novelty-risk fields
ID | Paper / System | Year | Venue | Primary Theme | Mechanism | Latency Target | Hardware / Model Regime | Datasets | Key Reported Result | PACER Overlap | Novelty Risk | What PACER Can Learn | Limitation / Open Gap | Source / DOI / arXiv | Verification Status | Priority
L01 | Predictive Prefetching for Retrieval-Augmented Generation | 2026 | ICML | Predictive retrieval | Predict when retrieval should trigger and what to retrieve | E2E / TTFT | Llama-3.1-8B; server GPU | RAG workloads / traces | Up to 43.5% E2E and 62.4% TTFT reduction | High: prediction + retrieval timing | High | Predictor target, oracle traces, false-positive accounting | Trace dependence; predictor errors can waste work | https://proceedings.mlr.press/v306/zhang26f.html | Verified | Critical
L02 | TeleRAG | 2026 | MLSys | Lookahead retrieval | Retrieve future context during generation | E2E | RTX 4090; Llama-3.2-3B / Llama-3-8B | NQ, HotpotQA, TriviaQA | ~1.98× E2E improvement reported in prior analysis | High: lookahead + local GPU | High | Consumer-GPU implementation and overlap measurement | Strong overlap baseline; narrows naive PACER novelty | https://github.com/TeleRAG/TeleRAG | Verified | Critical
L03 | CacheBlend | 2025 | EuroSys | KV cache reuse | Reuse cached chunks; selective recomputation + pipelining | TTFT / throughput | Data-center GPU; long-context RAG | RAG workloads | 2.2–3.3× TTFT; 2.8–5× throughput | High: KV reuse + overlap | High | Selective recompute and cache accounting | Different serving assumptions; compare carefully | https://www.usenix.org/conference/eurosys2025/presentation/yao | Verified | Critical
L04 | RAGCache | 2024 | arXiv | Hierarchical caching | Knowledge-tree multilevel cache + overlap | TTFT / throughput | GPU/host hierarchy | RAG workloads | Up to 4× TTFT; 2.1× throughput | Medium-High | Medium | Cache hierarchy and eviction ideas | Different workload/system design | https://arxiv.org/abs/2404.12457 | Verified | High
L05 | TurboRAG | 2025 | EMNLP | Chunk KV caching | Precompute chunk KV; stitch with attention/reordered RoPE | TTFT | LLM inference | Long-context/RAG | Up to 9.4× TTFT | High | High | Chunk-level reuse baseline | Strong specialized cache mechanism | https://aclanthology.org/2025.emnlp-main.336/ | Verified | Critical
L06 | ECoRAG | 2025 | Findings ACL | Adaptive compression | Evidentiality-guided compression + retrieve more if insufficient | Quality / latency | RAG LLM | QA/RAG | Compression-quality tradeoff | High: adaptive evidence retention | High | Evidence sufficiency signal | Compression mechanism itself is established | https://aclanthology.org/2025.findings-acl.1371/ | Verified | Critical
L07 | ACC-RAG | 2025 | Findings EMNLP | Adaptive compression | Query-complexity-conditioned compression rate | Latency | RAG LLM | QA/RAG | >4× faster inference claim | High | High | Query-conditioned budget allocation | Direct overlap with adaptive compression | https://aclanthology.org/2025.findings-emnlp.1368/ | Verified | Critical
L08 | CORE-RAG | 2026 | ICML | Performance-driven compression | Performance-driven learning + distillation | Quality / context reduction | RAG LLM | QA/RAG | 3% compressed context with reported +3.3 EM | Medium-High | Medium | Performance-driven selection objective | Not primarily a systems coordination paper | https://proceedings.mlr.press/v306/cui26a.html | Verified | High
L09 | SpecCache | 2026 | ACL | Speculative KV reuse | Speculative KV cache reuse for RAG serving | TTFT | LLM serving | RAG workloads | Efficient reuse | High | High | Cache reuse as one action in policy | Need direct controlled comparison | https://aclanthology.org/2026.acl-long.921/ | Verified | High
L10 | REFRAG | 2025 | arXiv | Context compression / expansion | Compress, sense, expand RAG decoding | TTFT / context | LLM inference | Long-context RAG | 30.85× TTFT claim on arXiv | Medium | Medium | Alternative compressed-representation regime | Different architecture; not direct systems baseline | https://arxiv.org/abs/2509.01092 | Verified | Medium
L11 | FusionRAG | 2026 | SIGMOD | Fusion cache | Offline cross-chunk embedding + selective KV recompute | TTFT | LLM serving | RAG workloads | 2.66×–9.39× TTFT reported | High | High | Cross-chunk cache/recompute baseline | Strong overlap; must distinguish policy from mechanism | https://doi.org/10.1145/3786655 | Verified | Critical
L12 | CacheTune | 2026 | arXiv | Adaptive KV reuse | Frequency-guided + hardware-aware reuse | TTFT / throughput | GPU + storage | Long-context serving | 3.72–4.86× TTFT reported | High | High | Hardware-aware action selection | Not explicitly joint retrieval+compression policy | https://arxiv.org/abs/2605.24022 | Verified | Critical
L13 | PCR | 2026 | arXiv | Prefetch + cache | Prefix tree, look-ahead LRU, SSD→DRAM prefetch | TTFT | Storage hierarchy | RAG serving | Up to 2.47× TTFT | High | High | Pending-request-aware prefetch | System-level overlap already explored | https://arxiv.org/abs/2603.23049 | Verified | High
L14 | HedraRAG | 2025 | arXiv | Serving coordination | Graph-based runtime + CPU/GPU pipeline | E2E / throughput | Heterogeneous serving | RAG workloads | >1.5× to 5× claims | High | High | Coordination framing | System optimizer overlaps conceptually | https://arxiv.org/abs/2507.09138 | Verified | High
L15 | RAGO | 2025 | arXiv | RAG serving optimizer | Schema + optimizer for RAG execution | QPS / TTFT | Serving systems | RAG workloads | Up to 2× QPS/chip; 55% TTFT reduction | High | High | System-level objective formulation | Different scope and optimizer abstraction | https://arxiv.org/abs/2503.14649 | Verified | High
L16 | CoinRAG | 2026 | arXiv | Fine-grained KV reuse | Semantic information-nugget KV caches | Quality / latency | Long-context RAG | RAG QA | 5.3% relative F1 under fast-prefill budget | High | High | Fine-grained reuse action | Very recent; direct overlap with compressed nugget cache | https://arxiv.org/abs/2608.07458 | Verified | Critical
L17 | VoiceAgentRAG | 2026 | arXiv | Predictive prefetch | Slow thinker predicts follow-up topics; foreground cache | E2E | Agent/voice RAG | Conversational tasks | Background prefetch for latency | Medium-High | Medium-High | Prediction + cache interaction | Different agent/voice workload | https://arxiv.org/abs/2603.02206 | Verified | High

## 03_Dataset_Registry
PACER Dataset Registry
Dataset size, access, role, and multimodal extension planning
ID | Dataset | Modality | Task / Role | Approx. Size | Evidence Type | Primary Use in PACER | Public / Private | License / Access Note | Recommended Split / Sampling | Latency Stress Potential | Multimodal Extension | Official / Source Link | Status | Priority
D01 | HotpotQA | Text | Multi-hop QA / retrieval | ~113K questions | Gold supporting facts + docs | Core multi-hop latency benchmark | Public | Research dataset; verify current terms | Dev/test; controlled retrieval depth | High | No | https://hotpotqa.github.io/ | Candidate | Critical
D02 | 2WikiMultihopQA | Text | Multi-hop QA | 192,606 examples | Evidence paths | Core multi-hop benchmark | Public | Research benchmark | Fixed test subset + sampled train traces | High | No | https://github.com/Alab-NII/2wikimultihop | Candidate | Critical
D03 | Natural Questions | Text | Open-domain QA | 307,372 train; 7,830 dev; 7,842 test | Wikipedia evidence | Large-scale retrieval baseline | Public | Google Research dataset | Use official dev/test; sampled training traces | High | No | https://ai.google.com/research/NaturalQuestions/ | Candidate | Critical
D04 | TriviaQA | Text | QA + evidence retrieval | ~95K QA pairs; >650K QA-evidence triples | Web evidence | Diverse retrieval baseline | Public | Research dataset; verify terms | Official split | High | No | https://nlp.cs.washington.edu/triviaqa/ | Candidate | High
D05 | LongBench | Text | Long-context evaluation | 21 datasets | Long-context inputs | Generation-dominant/local regime stress test | Public | Benchmark with task-specific data terms | English subset + selected tasks | Very High | No | https://github.com/THUDM/LongBench | Candidate | Critical
D06 | DocVQA | Visual | Document visual QA | ~50K questions; 12K+ images | Document images + QA | Multimodal extension | Public | Dataset-specific terms | Official validation/test where available | High | Yes | https://www.docvqa.org/ | Candidate | High
D07 | MP-DocVQA | Visual | Multi-page document QA | ~46,436 questions; 5,929 docs | Multi-page docs | Cross-page retrieval/compression | Public | Dataset-specific terms | Validation/test | Very High | Yes | https://www.docvqa.org/datasets | Candidate | High
D08 | InfographicVQA | Visual | Infographic QA | 30,035 questions; 5,485 images | Infographics + QA | Visual evidence selection | Public | Dataset-specific terms | Official splits | High | Yes | https://rrc.cvc.uab.es/?ch=17 | Candidate | Medium
D09 | SlideVQA | Visual | Slide-deck QA | 2.6K+ decks; 52K+ slides; 14.5K questions | Slide images + text | Long visual context | Public | Dataset-specific terms | Official split | Very High | Yes | https://github.com/nttmdlab-nlp/SlideVQA | Candidate | High
D10 | ChartQA | Visual | Chart QA | ~32.7K questions | Charts + questions | Structured visual evidence | Public | Dataset-specific terms | Official test | Medium-High | Yes | https://github.com/vis-nlp/ChartQA | Candidate | Medium
D11 | ChartQAPro | Visual | Hard chart QA | 1,948 questions; 1,341 charts; 157 sources | Diverse charts | Hard multimodal stress test | Public | Research benchmark | Official split | High | Yes | https://arxiv.org/abs/2504.05506 | Candidate | Medium
D12 | MMLongBench-Doc | Visual | Long-document understanding | Long visual documents | Cross-page evidence | Multimodal long-context extension | Public | Research-use / CC BY-NC 4.0 per repo; verify | Research split | Very High | Yes | https://github.com/haoosz/MMLongBench | Candidate | High
D13 | ViDoRe | Visual retrieval | Visual document retrieval | Multiple benchmark subsets | Multi-vector visual retrieval | Retrieval-side multimodal evaluation | Public | Collection-specific terms | Selected V3 subsets | High | Yes | https://github.com/illuin-tech/vidore-benchmark | Candidate | High
D14 | MuSiQue | Text | Multi-hop QA | ~25K examples | Compositional reasoning | Optional hard multi-hop benchmark | Public | Dataset terms | Dev/test | High | No | https://github.com/StonyBrookNLP/musique | Candidate | Medium
D15 | Private institutional corpus | Text / Visual | Domain-specific retrieval | TBD after authorization | Internal documents | Optional real-world validation | Private | Only with explicit institutional authorization | Documented sampled evaluation set | Very High | Yes | Internal / access-controlled | Optional | Medium

## 04_Baseline_Catalog
Baseline Catalog
Comparable systems and component baselines to prevent weak novelty claims
ID | Baseline | Category | What It Tests | Expected Strength | PACER Comparison | Implementation Risk | Hardware Match | Must Reproduce? | Evidence / Source | Status
B01 | Standard RAG | Reference | No prediction/compression/cache | Weak latency baseline | Absolute reference | Low | High | Yes | — | Planned
B02 | Predictive Prefetching | Predictive retrieval | Retrieval timing prediction | Very strong | Predictor-only component | Medium | Medium | Yes | ICML 2026 | Planned
B03 | TeleRAG | Lookahead retrieval | Consumer-GPU lookahead | Very strong | Lookahead baseline | Medium | Very High | Yes | MLSys 2026 / GitHub | Planned
B04 | ECoRAG | Compression | Evidence-guided compression | Strong | Compression-only | Medium | Medium | Yes | ACL Findings 2025 | Planned
B05 | ACC-RAG | Compression | Query-conditioned compression rate | Strong | Adaptive compression-only | Medium | Medium | Yes | EMNLP Findings 2025 | Planned
B06 | CacheBlend | KV reuse | Selective recompute + cache | Very strong | Reuse-only | High | Medium | Yes | EuroSys 2025 | Planned
B07 | TurboRAG | KV reuse | Chunk KV precompute/stitch | Very strong | Fast cache baseline | High | Medium | Yes | EMNLP 2025 | Planned
B08 | FusionRAG | Fusion cache | Cross-chunk offline + selective online recompute | Very strong | Cache/recompute baseline | High | Medium | Yes | SIGMOD 2026 | Planned
B09 | CacheTune | Adaptive KV reuse | Hardware-aware reuse ratio | Very strong | Adaptive reuse baseline | High | High | Yes | arXiv 2026 | Planned
B10 | RAGO / HedraRAG | System coordination | System-level optimization/coordination | Strong | Coordination baseline | High | Medium | If feasible | arXiv 2025 | Planned

## 05_Experiment_Matrix
Experiment Matrix
End-to-end experiment plan with explicit comparison controls and evidence targets
Exp ID | Stage | Dataset | Model | Retriever | Retrieval Top-k | Compression | Cache / Reuse | Prediction | Latency Budget | Hardware | Seeds | Primary Metrics | Secondary Metrics | Expected Evidence | Status | Priority
E01 | Calibration | HotpotQA | Qwen3-8B | BM25+dense | 5 | None | None | None | Unconstrained | 24GB GPU | 3 | TTFT; E2E; EM/F1 | GPU memory; tokens/s | Reference profile | Planned | Critical
E02 | Baseline | HotpotQA | Qwen3-8B | BM25+dense | 5 | None | None | None | Unconstrained | 24GB GPU | 3 | TTFT; E2E | P95; memory | Standard RAG baseline | Planned | Critical
E03 | Baseline | HotpotQA | Qwen3-8B | BM25+dense | 5 | None | None | Lookahead | Unconstrained | 24GB GPU | 3 | TTFT; E2E | Wasted prefetch | Predictor/lookahead effect | Planned | Critical
E04 | Baseline | HotpotQA | Qwen3-8B | BM25+dense | 5 | Adaptive | None | None | Fixed | 24GB GPU | 3 | E2E; EM/F1 | Compression overhead | Compression effect | Planned | Critical
E05 | Baseline | HotpotQA | Qwen3-8B | BM25+dense | 5 | None | KV reuse | None | Unconstrained | 24GB GPU | 3 | TTFT; E2E | Hit/recompute rate | Cache effect | Planned | Critical
E06 | Integration | HotpotQA | Qwen3-8B | BM25+dense | 5 | Adaptive | KV reuse | Lookahead | Fixed | 24GB GPU | 5 | TTFT; E2E; EM/F1 | P95/P99; memory; overhead | Full PACER candidate | Planned | Critical
E07 | Integration | 2WikiMultihopQA | Llama-3.2-3B | BM25+dense | 5 | Adaptive | KV reuse | Lookahead | Fixed | 24GB GPU | 5 | TTFT; E2E; EM/F1 | wasted work | Cross-model generalization | Planned | Critical
E08 | Integration | NQ | Llama-3.2-8B | Dense | 10 | Adaptive | KV reuse | Lookahead | Fixed | 24GB GPU | 5 | TTFT; E2E; EM/F1 | memory; throughput | Open-domain generalization | Planned | High
E09 | Stress | LongBench | Qwen3-8B | Dense | 10 | Adaptive | KV reuse | Lookahead | Tight | 24GB GPU | 5 | TTFT; E2E | P95/P99; context length | Generation-dominant regime | Planned | Critical
E10 | Ablation | HotpotQA | Qwen3-8B | BM25+dense | 5 | Adaptive | None | Lookahead | Fixed | 24GB GPU | 5 | E2E; EM/F1 | overhead | Prediction + compression synergy | Planned | Critical
E11 | Ablation | HotpotQA | Qwen3-8B | BM25+dense | 5 | None | KV reuse | Lookahead | Fixed | 24GB GPU | 5 | TTFT; E2E | cache hits | Prediction + cache synergy | Planned | Critical
E12 | Ablation | HotpotQA | Qwen3-8B | BM25+dense | 5 | Adaptive | KV reuse | None | Fixed | 24GB GPU | 5 | TTFT; E2E | quality; recompute | Compression + cache synergy | Planned | Critical
E13 | Policy | HotpotQA | Qwen3-8B | BM25+dense | 5 | Adaptive | KV reuse | Lookahead | Adaptive | 24GB GPU | 5 | E2E; EM/F1 | policy entropy; action cost | Joint resource allocation | Planned | Critical
E14 | Policy | 2WikiMultihopQA | Qwen3-8B | BM25+dense | 5 | Adaptive | KV reuse | Lookahead | Adaptive | 24GB GPU | 5 | E2E; EM/F1 | budget utilization | Adaptive policy generalization | Planned | High
E15 | Multimodal | DocVQA | Vision-Language model | Visual retrieval | 5 | Adaptive visual | Visual cache | Lookahead | Adaptive | 24GB GPU | 3 | E2E; ANLS | VRAM; retrieval latency | Multimodal extension feasibility | Optional | Medium
E16 | Multimodal | MP-DocVQA | Vision-Language model | Visual retrieval | 5 | Adaptive visual | Visual cache | Lookahead | Adaptive | 24GB GPU | 3 | E2E; ANLS | cross-page hits | Long visual context | Optional | Medium
E17 | Pareto | LongBench | Qwen3-8B | Dense | 10 | Adaptive | KV reuse | Lookahead | Adaptive | 24GB GPU | 5 | Quality vs E2E | TTFT; memory | Pareto frontier | Planned | Critical
E18 | Repro | HotpotQA | Qwen3-8B | BM25+dense | 5 | Adaptive | KV reuse | Lookahead | Adaptive | 24GB GPU | 10 | Median + CI | All telemetry | Reproducibility run | Planned | Critical

## 06_Ablation_Matrix
Ablation Matrix
Controlled component isolation; designed to test interaction/super-additivity rather than component novelty
Ablation | Predictor | Lookahead | Compression | KV Reuse | Joint Policy | Question Answered | Primary Metric | Expected Outcome | Decision Rule | Status
S0 Standard RAG | No | No | No | No | No | Reference latency/quality | E2E | Baseline | Required reference | Planned
S1 Prediction + Lookahead | Yes | Yes | No | No | No | Does prediction reduce retrieval stalls? | TTFT/E2E | Improves vs S0 | Paired significance | Planned
S2 Adaptive Compression | No | No | Yes | No | No | Does adaptive compression reduce latency at fixed quality? | E2E/quality | Improves Pareto | Quality non-inferiority | Planned
S3 Selective KV Reuse | No | No | No | Yes | No | Does reuse reduce TTFT? | TTFT | Improves | Hit/recompute accounting | Planned
S4 Prediction + Compression | Yes | Yes | Yes | No | No | Is prediction useful when compression changes compute? | E2E | Potential synergy | Interaction effect | Planned
S5 Compression + KV Reuse | No | No | Yes | Yes | No | Does compressed representation improve reuse? | TTFT/E2E | Potential synergy | Interaction effect | Planned
S6 Predictor + KV Reuse | Yes | Yes | No | Yes | No | Does lookahead complement cache reuse? | TTFT/E2E | Potential synergy | Interaction effect | Planned
S7 Full PACER | Yes | Yes | Yes | Yes | Yes | Does joint resource allocation beat best component combination? | E2E/quality | Best Pareto frontier | Predefined significance + effect size | Planned

## 07_Metrics_Spec
Metrics & Measurement Specification
Definitions designed to make PACER comparisons reproducible and statistically defensible
Metric | Definition | Why It Matters | Measurement Method | Unit | Primary / Secondary | Target / Interpretation | Pitfall to Avoid
TTFT | Time to first generated token | Retrieval/prefill latency | Wall-clock from request acceptance to first token | ms | Primary | Lower is better | Do not mix queueing and model-only timings without labels
E2E latency | Request start to final token | User-visible latency | Wall-clock end-to-end | ms | Primary | Lower is better | Report token count and output length
P50/P95/P99 | Latency percentiles | Tail behavior | Across repeated requests | ms | Primary | Lower is better | Avoid small-N percentile claims
Tokens/s | Generation throughput | Generation regime | Generated tokens / generation time | tok/s | Secondary | Higher is better | Separate prefill from decode if possible
EM / F1 / ROUGE-L | Answer quality | Quality preservation | Dataset evaluator | score | Primary | No unacceptable degradation | Use task-appropriate metric
Compression ratio | Original tokens / retained tokens | Compression efficiency | Count before/after compression | × | Secondary | Higher with quality retained | Account for compressor overhead
Cache hit rate | Reusable requests/chunks / eligible | Cache effectiveness | Telemetry | % | Secondary | Higher can help | Hit rate alone does not prove speedup
Wasted prefetch | Prefetched evidence not used | Predictor cost | Unused prefetched retrievals / all prefetches | % | Primary | Lower is better | Count both retrieval and downstream processing cost
Recompute ratio | Tokens recomputed / cached candidate tokens | Reuse selectivity | Telemetry | % | Primary | Lower if quality maintained | Cache reuse can hurt quality if too aggressive
GPU memory peak | Maximum allocated/used memory | Consumer-GPU feasibility | Framework + nvidia-smi telemetry | GB | Primary | Must fit budget | Include allocator overhead where possible
Policy overhead | Time spent making allocation decisions | Net benefit of controller | Controller wall time | ms | Primary | Small relative to savings | Do not hide CPU-side overhead
Pareto score | Quality vs latency frontier | Overall decision criterion | Non-dominated configurations | frontier | Primary | Prefer frontier, not single metric | Do not collapse quality into arbitrary scalar only

## 08_Risk_Register
Risk Register
Threats to novelty, validity, feasibility, and reproducibility
Risk ID | Risk | Likelihood | Impact | Early Warning | Mitigation | Fallback | Owner | Status
R01 | Novelty overlap with predictive prefetch/cache/compression papers | High | High | New paper claims same combination | Frame novelty as joint resource-allocation policy + controlled interaction study | Narrow to allocation objective + local regime | Research lead | Open
R02 | Consumer GPU cannot co-reside all modules | High | High | VRAM OOM / fragmentation | Measure memory per module; use offload/quantization; staged execution | Evaluate policy with selected components separately | Systems | Open
R03 | Predictor overhead cancels retrieval savings | Medium | High | Controller latency > saved stall time | Budget-aware predictor; lightweight features; profile CPU/GPU overlap | Oracle upper-bound + no-predictor baseline | ML | Open
R04 | Compression harms answer quality | Medium | High | EM/F1 drops beyond tolerance | Use quality-constrained adaptive budget | Use weaker compression setting | ML | Open
R05 | Trace collection is expensive | Medium | Medium | Oracle retrieval labels costly | Start with 5–10K traces; active sampling; cache traces | Use heuristic/oracle ablation | Data | Open
R06 | Baselines use incompatible hardware/software | High | High | Cannot reproduce published speedups | Normalize model, batch, retrieval, output length, hardware where feasible | Report apples-to-apples local subset | Systems | Open
R07 | Dataset licensing/access blocks evaluation | Low-Medium | Medium | Download/access restrictions | Track license/access in Dataset Registry | Substitute public dataset with same task profile | Data | Open
R08 | Results depend on one model | Medium | Medium | Large variance across models | Use Qwen3-8B + Llama-3.2-3B/8B | Report model-specific conclusions | Evaluation | Open

## 09_Trace_Schema
Trace Schema
Minimum telemetry fields needed for causal/paired latency analysis and reproducibility
Field | Type | Example | Required? | Purpose
request_id | string | hpqa_000123 | Yes | Unique experiment request
dataset | string | HotpotQA | Yes | Dataset identifier
model | string | Qwen3-8B | Yes | Local LLM/VLM
query_tokens | integer | 46 | Yes | Input length
retrieved_chunks | integer | 5 | Yes | Retrieved evidence count
retrieval_start_ms | float | 12.4 | Yes | Retrieval timing
retrieval_end_ms | float | 31.8 | Yes | Retrieval timing
prefetch_trigger_ms | float | 8.2 | If predictive | Prediction timing
prefetch_used | boolean | TRUE | If predictive | Wasted prefetch calculation
compression_start_ms | float | 34 | If compression | Compressor overhead
tokens_before | integer | 2200 | If compression | Compression ratio
tokens_after | integer | 780 | If compression | Compression ratio
cache_hit | boolean | TRUE | If cache | Reuse accounting
recompute_tokens | integer | 160 | If cache | Selective recomputation
ttft_ms | float | 410.2 | Yes | Primary latency
e2e_ms | float | 2150.8 | Yes | Primary latency
output_tokens | integer | 118 | Yes | Normalize generation cost
gpu_mem_peak_gb | float | 18.4 | Yes | Consumer GPU feasibility
policy_overhead_ms | float | 1.8 | If policy | Net controller cost
answer_metric | float | 0.72 | Yes | Quality score

## 10_Hypotheses
Hypothesis Register
Pre-registered-style hypotheses and falsification conditions
ID | Hypothesis | Independent Variable | Dependent Variable | Expected Direction | Falsification Condition | Experiment IDs | Status
H1 | Prediction-conditioned retrieval reduces wasted prefetch without degrading quality | Prediction policy | Wasted prefetch; E2E; quality | ↓ waste; ↓ E2E; ≈ quality | No significant E2E gain or waste reduction | E03,E06,E13 | Planned
H2 | Adaptive compression improves the latency-quality Pareto frontier | Compression budget policy | E2E; EM/F1; compression ratio | ↓ latency at matched quality | Quality loss exceeds predefined tolerance | E04,E06,E17 | Planned
H3 | Selective KV reuse reduces TTFT when cache hits are sufficiently high | Reuse policy | TTFT; hit rate | ↓ TTFT | No TTFT improvement after overhead | E05,E12 | Planned
H4 | Joint policy yields non-additive benefits by coordinating competing compute/memory actions | Joint allocation policy | E2E; Pareto; interaction effect | Better frontier than best single component | No interaction / no frontier improvement | S4–S7,E13,E17 | Planned
H5 | Local generation-heavy workloads reduce the relative benefit of retrieval-only optimization | Workload regime | Latency decomposition | Retrieval share ↓; generation share ↑ | Retrieval remains dominant across long outputs | E09,E17 | Planned

## 11_References
Reference List
Compact bibliographic register for the literature matrix
Ref ID | Citation | Topic | Year | Type | URL / DOI | Used In
R01 | Zhang & Pei. Predictive Prefetching for Retrieval-Augmented Generation. ICML 2026. | Predictive retrieval | 2026 | Conference | https://proceedings.mlr.press/v306/zhang26f.html | Literature; Baselines
R02 | TeleRAG: Efficient retrieval-augmented generation inference with lookahead retrieval. MLSys 2026. | Lookahead retrieval | 2026 | Conference | https://github.com/TeleRAG/TeleRAG | Literature; Baselines
R03 | Yao et al. CacheBlend: Fast Large Language Model Serving for RAG with Cached Knowledge. EuroSys 2025. | KV cache | 2025 | Conference | https://www.usenix.org/conference/eurosys2025/presentation/yao | Literature; Baselines
R04 | Jin et al. RAGCache: Efficient Knowledge Caching for Retrieval-Augmented Generation. arXiv:2404.12457. | Caching | 2024 | Preprint | https://arxiv.org/abs/2404.12457 | Literature
R05 | Lu et al. TurboRAG: Accelerating Retrieval-Augmented Generation with Precomputed KV Caches. EMNLP 2025. | KV cache | 2025 | Conference | https://aclanthology.org/2025.emnlp-main.336/ | Literature; Baselines
R06 | Jeong et al. ECoRAG: Evidentiality-guided Compression for Retrieval-Augmented Generation. Findings ACL 2025. | Compression | 2025 | Conference | https://aclanthology.org/2025.findings-acl.1371/ | Literature; Baselines
R07 | Guo et al. ACC-RAG: Adaptive Context Compression for Retrieval-Augmented Generation. Findings EMNLP 2025. | Compression | 2025 | Conference | https://aclanthology.org/2025.findings-emnlp.1368/ | Literature; Baselines
R08 | Cui et al. Less Is More: Elevating RAG via Performance-Driven Context Compression. ICML 2026. | Compression | 2026 | Conference | https://proceedings.mlr.press/v306/cui26a.html | Literature
R09 | Wen et al. SpecCache: Speculative KV Cache Reuse for Efficient RAG Serving. ACL 2026. | KV reuse | 2026 | Conference | https://aclanthology.org/2026.acl-long.921/ | Literature
R10 | Lin et al. REFRAG: Rethinking RAG based on Compression and Expansion. arXiv:2509.01092. | Compression/decoding | 2025 | Preprint | https://arxiv.org/abs/2509.01092 | Literature
R11 | Wang et al. From Prefix Cache to Fusion RAG Cache: Accelerating LLM Inference in RAG. SIGMOD 2026. | Cache/recompute | 2026 | Conference | https://doi.org/10.1145/3786655 | Literature; Baselines
R12 | Li et al. CacheTune: Adaptive KV Cache Reuse for Fast Long-Context LLM Serving. arXiv:2605.24022. | KV reuse | 2026 | Preprint | https://arxiv.org/abs/2605.24022 | Literature; Baselines
R13 | Wang et al. PCR: A Prefetch-Enhanced Cache Reuse System for Low-Latency RAG Serving. arXiv:2603.23049. | Prefetch/cache | 2026 | Preprint | https://arxiv.org/abs/2603.23049 | Literature
R14 | Hu et al. HedraRAG: Coordinating LLM Generation and Database Retrieval in Heterogeneous RAG Serving. arXiv:2507.09138. | System coordination | 2025 | Preprint | https://arxiv.org/abs/2507.09138 | Literature
R15 | Jiang et al. RAGO: Systematic Performance Optimization for Retrieval-Augmented Generation Serving. arXiv:2503.14649. | Serving optimizer | 2025 | Preprint | https://arxiv.org/abs/2503.14649 | Literature
R16 | Kim et al. CoinRAG: Contextualized Information Nugget KV Cache Reuse for Long-Context RAG. arXiv:2608.07458. | Fine-grained KV | 2026 | Preprint | https://arxiv.org/abs/2608.07458 | Literature
R17 | Qiu et al. VoiceAgentRAG. arXiv:2603.02206. | Predictive agent retrieval | 2026 | Preprint | https://arxiv.org/abs/2603.02206 | Literature

## 12_Novelty_Map
Novelty Map
The most important sheet: prevents overclaiming and turns the literature gap into a defensible research contribution
Capability | Existing Literature | PACER Position | Novelty Strength | How to Defend | Evidence Needed
Predictive retrieval timing | Predictive Prefetching; TeleRAG; VoiceAgentRAG | Use as an established primitive inside controller | Low alone | Explicitly disclaim primitive novelty | Reproduction + error/waste analysis
Adaptive compression | ECoRAG; ACC-RAG; CORE-RAG | Use as established action with latency/quality budget | Low alone | Focus on joint budget allocation | Matched-quality latency curves
KV cache reuse | CacheBlend; TurboRAG; SpecCache; CacheTune; FusionRAG; CoinRAG | Use as established action | Low alone | Do not call compressed cache a new primitive | Cache/recompute telemetry
System coordination | RAGO; HedraRAG; PCR | PACER specializes coordination around retrieval/compression/reuse on local GPU | Medium | Define explicit action space + objective + policy | Policy ablation and interaction analysis
Single consumer-GPU regime | TeleRAG already tests RTX 4090 | Use as controlled evaluation regime, not sole novelty | Medium-low | Emphasize generation-dominant and memory-constrained analysis | Latency decomposition + memory
Joint resource allocation | Pieces exist separately; no established identical policy in this reviewed set | Predict-conditioned action selection under common latency-quality budget | Potentially High | Formalize state, action, cost, reward/constraint and compare against best-component oracle | Interaction effect + Pareto frontier + cross-model generalization
Super-additivity / interaction study | Most systems report component/system gains, but controlled interaction evidence varies | Test whether components complement or cannibalize each other | Potentially High | Predefine interaction/falsification criteria | S0–S7 + statistical tests

## 13_Reproducibility
Reproducibility Checklist
Minimum artifact and measurement details required for a strong systems/ML paper
Item | Required Detail | Recorded Where | Status | Notes
Hardware | GPU model, VRAM, CPU, RAM, storage | Experiment Matrix / run logs | Planned | Consumer GPU is central
Software | OS, CUDA, driver, PyTorch, transformers, retrieval library | Run metadata | Planned | Pin versions
Model | Exact checkpoint + quantization | Experiment Matrix | Planned | Record commit/hash where possible
Retriever | Index type, embedding model, chunk size, top-k | Experiment Matrix | Planned | Same retrieval config across baselines
Generation | Temperature, max new tokens, stopping criteria | Run config | Planned | Keep output length controlled
Seeds | All random seeds | Run metadata | Planned | ≥3 for main, ≥5 critical comparisons
Warmup | Number of warmup requests | Run config | Planned | Separate cold-start and warm-cache results
Timing | Synchronization method + clock source | Run config | Planned | CUDA synchronization where needed
Memory | Peak allocated/reserved and nvidia-smi peak | Trace schema | Planned | Report both when relevant
Statistics | Paired bootstrap, Wilcoxon, Holm correction | Analysis notebook | Planned | Report CI + effect size
Artifact | Code, configs, traces, result CSVs | Repository / artifact | Planned | Release only legally shareable data